## Defect Reports
OrangeHRM Defect Reports
Defect ID | Category | Module | Summary | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reported By | Reported Date
BUG-001 | Bug | Login | Session timeout redirects unexpectedly | User is logged out during active navigation | Login, navigate between modules for 15+ mins | Active session maintained | Redirected to login page with token error | High | High | Assigned | Parth QA | 2026-06-02
BUG-002 | Bug | Dashboard | Widgets load slowly | Dashboard takes excessive time to render | Login and open dashboard | Dashboard loads within acceptable time | Widgets load after noticeable delay | Medium | Medium | In Progress | Parth QA | 2026-06-03
BUG-003 | Bug | PIM | Employee save validation issue | Invalid data accepted in employee form | Enter invalid phone format and save | Validation message displayed | Record saved successfully | High | High | Open | Parth QA | 2026-06-04
BUG-004 | Bug | Leave | Leave balance mismatch | Displayed balance differs from calculated value | Apply leave and review balance | Correct balance displayed | Balance reduced incorrectly | Critical | Critical | Fixed | Parth QA | 2026-06-05
OBS-001 | Observation | Directory | Search UX improvement | Search requires exact text match | Search employee with partial name | Relevant suggestions shown | Limited search flexibility | Low | Low | Closed | Parth QA | 2026-06-06
OBS-002 | Observation | Logout | Logout confirmation missing | System logs out immediately | Click logout | Confirmation dialog displayed | Immediate logout | Low | Medium | Open | Parth QA | 2026-06-07
ENH-001 | Enhancement | Admin | Bulk user import | Need CSV import for user management | Review user creation workflow | Bulk upload available | Only manual creation available | Medium | Medium | Assigned | Parth QA | 2026-06-08
ENH-002 | Enhancement | Recruitment | Resume preview | Preview candidate resume before download | Open candidate profile | Inline preview available | Download required | Low | Low | In Progress | Parth QA | 2026-06-09
BUG-005 | Bug | Recruitment | Candidate status update fails | Status not saved consistently | Update candidate status | Status saved | Intermittent failure | Medium | High | Retest | Parth QA | 2026-06-10
BUG-006 | Bug | Admin | Role permission inconsistency | Restricted menu visible to user role | Login as limited role | Restricted menus hidden | Menu visible | Critical | Critical | Closed | Parth QA | 2026-06-11

## Bug Tracking Log
OrangeHRM Bug Tracking Log
Defect ID | Module | Reported By | Assigned To | Created Date | Fixed Date | Retest Date | Current Status | Comments
BUG-001 | Login | Parth QA | Backend Team | 2026-06-02 |  |  | Assigned | Developer assigned and analysis started
BUG-002 | Dashboard | Parth QA | Frontend Team | 2026-06-03 |  |  | In Progress | Fix under development
BUG-003 | PIM | Parth QA | HRMS Team | 2026-06-04 |  |  | Open | Awaiting triage
BUG-004 | Leave | Parth QA | Backend Team | 2026-06-05 | 2026-06-08 | 2026-06-09 | Fixed | Code fix deployed to QA
OBS-001 | Directory | Parth QA | Frontend Team | 2026-06-06 |  |  | Closed | Verified and closed
OBS-002 | Logout | Parth QA | Frontend Team | 2026-06-07 |  |  | Open | Awaiting triage
ENH-001 | Admin | Parth QA | HRMS Team | 2026-06-08 |  |  | Assigned | Developer assigned and analysis started
ENH-002 | Recruitment | Parth QA | Frontend Team | 2026-06-09 |  |  | In Progress | Fix under development
BUG-005 | Recruitment | Parth QA | HRMS Team | 2026-06-10 |  | 2026-06-10 | Retest | Awaiting QA validation
BUG-006 | Admin | Parth QA | Backend Team | 2026-06-11 | 2026-06-11 |  | Closed | Verified and closed

## Severity vs Priority Analysis
OrangeHRM Severity vs Priority Analysis
Defect ID | Module | Severity | Priority | Reason
BUG-001 | Login | High | High | Affects user access continuity.
BUG-002 | Dashboard | Medium | Medium | Performance impacts usability.
BUG-003 | PIM | High | High | Data integrity risk in employee records.
BUG-004 | Leave | Critical | Critical | Incorrect leave balances affect business process.
OBS-001 | Directory | Low | Low | Usability improvement opportunity.
OBS-002 | Logout | Low | Medium | Minor user experience concern.
ENH-001 | Admin | Medium | Medium | Improves admin efficiency.
ENH-002 | Recruitment | Low | Low | Improves recruiter productivity.
BUG-005 | Recruitment | Medium | High | Recruitment workflow partially impacted.
BUG-006 | Admin | Critical | Critical | Security and access control exposure.
Severity Distribution |  |  | Priority Distribution
Critical | 2 |  | Critical | 2
High | 2 |  | High | 3
Medium | 3 |  | Medium | 3
Low | 3 |  | Low | 2
Severity Definitions |  |  | Priority Definitions
Critical | System unusable or security issue |  | Critical | Immediate fix required
High | Major functionality affected |  | High | Fix in next release
Medium | Partial functionality impacted |  | Medium | Fix during sprint
Low | Cosmetic or minor issue |  | Low | Can be deferred